## Sheet1
Bulkington Parish Council Maintenance Log 2025-26
|  |  |  | New Information | Work Completed | Action Pending
| Issue/Maintenance Task | Allocation (resp. Cllr) | Action taken
New – For review/decision
1 | Pipe in ditch opposite The Well | Cllr Breach | Asked Tamara to review the purchase of a pipe. Breach family offer to install. | Discussed at July meeting. Tamara to review. Possible cost £500.
2 | Latch gate of playground
Action for Parish Council
3 | Playground | Clerk | Playground equipment maintenance | Maintenance not done to standard. Meeting with Inspect & Repair on 06/06/2025 | Included in Maintenance plan | Awaiting quote for zip wire - may be condemned.
4 | White Entrance Gates for village
5
6

## LHFIG
In Progress | 06-22-32 | Bulkington | Bulkington Chestnut Drive - Request for Dropped Kerbs | There are slightly dropped kerbs at the end of the road . However these are sometimes obstructed by parked cars. The shaped curbs that do exist are unsuitable for manual wheelchair users. This is the only ramped access to the church (when cars are parked on the road for a service). The slightly dropped kerb to the right of the entrance is facing directly into the street sign – “Chestnut Drive” which makes it very difficult for motorised wheelchair users to negotiate onto the pavement as there is insufficient “turning access”. • Dropped kerbs at road height to be fitted at the end of Chestnut Drive. • These dropped kerbs should be indicated as ramp access so that cars are aware that they are disabled access routes. Parking restriction should be in place where there is ramp access • The street sign for Chestnut Drive should be relocated from the slightly dropped kerb | Order has been placed with contractor. Works require alterations to Utility apparatus (BT Chamber Cover). Milestone are seeking aggrement from BT. GR confirmed his team remains in contact with PC over the delay. Traffic Management issues due to the narrow carriageway and shallow depth of underground services in the area to be lowered. Therefore a revised cost estimate is being prepared. GR to liaise with the PC | In Progress | GR advised a budget of £2,000 for installation of a pair of dropped kerbs. PC to confirm contribution approval and rough plan/location description. DM suggested that this could be combined with other Bulkington dropped-kerb tasks to make efficient use of funds. GR suggested that they might all be delivered for £3,000. | 2023-01-17 | 40 | Devizes Rural West | Bulkington | 0:00 | 5
New Project | 06-22-33 | Bulkington | Bulkington Northfields - Request for Dropped Kerbs | There are no dropped curbs so when walking or wheeling up the high street, you can’t get up and down again from the pavements leaving into Northfields. The village has a lot of elderly, young children on scooters, parents with push chairs and wheelchair users. These areas make navigating their village very hard for them. Install a dropped kerb on both sides | PC to confirm budget contribution and proposed location. This fits the LHFIG and wider Council criteria and objectives on accesibility. | Linked to task above | Linked to task above | 2023-01-17 | 41 | Devizes Rural West | Bulkington | 0:00